Service Tray Monitor

Project Document

Charter · Statement of Work · WBS · Software Description · Defects · Tests · Change Control · Risks · Decisions · Configuration · Lessons Learned

| Field | Value |
| --- | --- |
| Project | Service Tray Monitor — Stabilisation and Documentation |
| Product release | 1.0.1 (defect-fix release; baseline 1.0.0) |
| Organisation | Miautrix |
| Document version | 0.1 — Draft for sponsor review |
| Date | 2026-09-13 |
| Framework | PMI — PMBOK® Guide practices |
| Source | docs/project/*.md in the miautrix-ServiceTrayMonitor repository |

Document control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0.1 | 2026-09-13 | Development team (AI-assisted, Claude Code) | Initial compilation from docs/project sources (artifacts 01–11) |

Contents

# 00 — About This Document and Governance

Source material for the formal project document of Service Tray Monitor (Miautrix), organised along PMI (PMBOK® Guide) practices. Each file is one project artifact. Together they are compiled into the project document, always issued as DOCX (DEC-012): ServiceTrayMonitor-Project-Document.docx.

| # | Artifact | File | PMI reference | Status |
| --- | --- | --- | --- | --- |
| 01 | Project Charter & Stakeholder Register | 01-project-charter.md | Initiating — Develop Project Charter, Identify Stakeholders | Draft — pending sponsor sign-off |
| 02 | Statement of Work & Scope Statement | 02-statement-of-work.md | Planning — Define Scope | Draft — pending sign-off |
| 03 | WBS & WBS Dictionary | 03-wbs.md | Planning — Create WBS | Current |
| 04 | Software Description (technical baseline) | 04-software-description.md | Product scope / Configuration baseline | Current (v1.0.1) |
| 05 | Defect Log | 05-defect-log.md | Executing / M&C — Issue log, Control Quality | Current |
| 06 | Test Plan, Test Report & Traceability Matrix | 06-test-plan-and-report.md | Plan/Control Quality, Requirements Traceability Matrix | Current |
| 07 | Change Request Log & CR Form | 07-change-request-log.md | M&C — Perform Integrated Change Control | Open |
| 08 | Risk Register | 08-risk-register.md | Planning / M&C — Risk management | Open |
| 09 | Decision & Assumption Log | 09-decision-log.md | Assumption log / Decision log | Current |
| 10 | Configuration Baseline & Release Record | 10-configuration-baseline.md | Configuration management | Current |
| 11 | Lessons Learned Register | 11-lessons-learned.md | Manage Project Knowledge | Open |

## Governance rules (agreed 2026-09-13)

- Statement of Work — the work started in the 2026-09-13 session: project analysis and knowledge base, defect testing and resolution, and preparation of this documentation.

- Defect fixes are part of the SoW under testing / solving. They restore documented or clearly intended behaviour and are tracked in the Defect Log.

- Changes — any new or altered functionality beyond intended behaviour — are Change Requests. They go through integrated change control (CR Log) and are not built until approved.

- Version control is GitHub. The GitHub app monitors the folder miautrix-ServiceTrayMonitor; its name and location must not change.

- PMI guidelines apply to planning, control, and closure artifacts.

## Conventions

| Prefix | Meaning | Status values |
| --- | --- | --- |
| DEF-nnn | Defect | New → Analysed → Fixed → Verified (automated) → Accepted (UAT) → Closed |
| CR-nnn | Change request | Submitted → Under analysis → Approved / Rejected / Deferred → Implemented → Closed |
| R-nn | Risk | Open → Mitigating → Closed / Occurred |
| DEC-nnn | Decision | Proposed → Confirmed / Superseded |
| AT-nn | Automated test group | Pass / Fail |
| UAT-nn | User acceptance test case | Not run → Pass / Fail / Blocked |
| LL-nn | Lesson learned | — |

Dates are ISO 8601 (YYYY-MM-DD). Placeholders that need client input are marked [TBD].

# 01 — Project Charter

| Field | Value |
| --- | --- |
| Project | Service Tray Monitor — Stabilisation and Documentation |
| Product | Service Tray Monitor (assembly ServiceTrayMonitor, installer SetupSTM) |
| Organisation | Miautrix |
| Charter date | 2026-09-13 |
| Document version | 0.1 (draft) |
| Sponsor | [TBD] |
| Project manager | [TBD] |

## 1. Purpose and business justification

Service Tray Monitor is a Windows system-tray application that lets administrators watch selected Windows services and start, stop, pause, and resume them. Version 1.0.0 is deployed and in use. Before new features are added, the product needs a verified technical baseline: a documented architecture, a list of known defects with fixes, automated tests, and a controlled way to handle future changes.

## 2. Objectives and success criteria

| # | Objective | Success criterion |
| --- | --- | --- |
| O1 | Understand and document the existing software | Knowledge base (graphify) and software description are published in the repository |
| O2 | Find and fix defects in v1.0.0 | Every logged defect has a root cause, a fix, and a verification reference; UAT accepted by the sponsor |
| O3 | Guarantee the app can control services with stored admin credentials | UAT-06 and UAT-07 pass on the target environment |
| O4 | Add a regression safety net | Automated test suite in the solution; 100 % pass on the release build |
| O5 | Establish project control | Change-request process, risk register, decision log, and configuration baseline in place |
| O6 | Prepare a releasable build | Version 1.0.1 builds with 0 errors/0 warnings; installer upgrades 1.0.0 in place |

## 3. High-level requirements

- Keep monitoring and control of Windows services from the tray icon and the main window.

- Keep the Admin Credentials capability: service actions must succeed when the app's own rights are refused and a valid admin account is saved (decision DEC-002).

- Settings and credentials persist in %AppData%\ServiceTrayMonitor\config.json; the password stays DPAPI-encrypted.

- The app keeps requiring administrator elevation (DEC-003).

- New functionality enters only through approved change requests.

## 4. High-level scope

In scope: see the Statement of Work — analysis and knowledge base, defect testing and resolution (v1.0.1), automated tests, installer corrections, and project documentation.

Out of scope: new features (for example CR-001, Restart action), product renaming (CR-002), code signing (CR-003), and deployment to production. All are handled through change control.

## 5. Summary milestones

| Milestone | Target date | Status |
| --- | --- | --- |
| M1 Analysis and knowledge base delivered | 2026-09-13 | Complete |
| M2 v1.0.0 configuration baseline captured | 2026-09-13 | Complete (zip + SHA-256 manifest) |
| M3 Defect fixes implemented and automated tests passing | 2026-09-13 | Complete |
| M4 Baseline and 1.0.1 committed to GitHub | [TBD] | Pending — client action |
| M5 User acceptance testing (UAT-01…UAT-12) | [TBD] | Not started |
| M6 Release 1.0.1 approved | [TBD] | Not started |
| M7 Feature planning (change requests) | After M3 | Pending — agreed to start after fixes |

## 6. Stakeholder register

| Stakeholder / role | Interest | Influence | Engagement / communication |
| --- | --- | --- | --- |
| Sponsor — [TBD] | Reliable service control, controlled change | High | Approves charter, CRs, UAT, release |
| Project manager — [TBD] | Scope, schedule, PMI artifacts | High | Owns logs; weekly status [TBD] |
| Product owner, Miautrix — [TBD] | Feature roadmap | High | Submits and prioritises CRs |
| IT administrators / operators (end users) | Day-to-day service control from the tray | Medium | UAT participants; release notes |
| Security / infrastructure owner — [TBD] | Credential storage, elevation, batch-logon rights, scheduled tasks | Medium | Reviews R-02, R-03, R-04 |
| Development team (AI-assisted engineering with Claude Code) | Implementation, tests, documentation | Medium | Delivers defect fixes and artifacts |

## 7. Assumptions and constraints

Assumptions

- A1 Target platform is Windows 10/11 or Windows Server with the .NET 8 Desktop Runtime (x64).

- A2 Operators run the app as an administrator (UAC prompt at launch).

- A3 Accounts saved under Admin Credentials have the "Log on as a batch job" right, which Administrators have by default.

- A4 Test accounts and a test machine will be provided for UAT.

Constraints

- C1 Source control is GitHub; the working folder miautrix-ServiceTrayMonitor must not be renamed or moved.

- C2 The installer is a Visual Studio Installer Project (.vdproj), built only inside Visual Studio.

- C3 No real services on production machines are changed during development testing.

## 8. High-level risks

See the Risk Register. Top risks: R-01 (credential path not yet verified with a real alternate account), R-03 (batch-logon right removed by policy), R-05 (no GitHub baseline commit yet).

## 9. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor | [TBD] |  |  |
| Project manager | [TBD] |  |  |

# 02 — Statement of Work and Scope Statement

| Field | Value |
| --- | --- |
| Project | Service Tray Monitor — Stabilisation and Documentation |
| SoW baseline date | 2026-09-13 |
| Document version | 0.1 (draft) |
| Product version in scope | 1.0.0 (baseline) → 1.0.1 (defect-fix release) |

## 1. Background

Service Tray Monitor v1.0.0 (C#/.NET 8 WinForms, MSI installer) is deployed and working. The client plans to add features. Before that, the client asked for (a) a full understanding of the project, captured in a knowledge base, (b) the problems found to be reported and solved, and (c) a project document following PMI guidelines.

## 2. Scope of work

### WP1 — Discovery, analysis, and knowledge base

- Review all source, project, manifest, and installer files.

- Build a knowledge graph with graphify (graphify-out/graph.html, GRAPH_REPORT.md, graph.json).

- Report findings and recommendations to the client before any change is made.

### WP2 — Defect testing and resolution ("testing / solving")

- Reproduce or confirm each defect and record its root cause (Defect Log).

- Fix defects so the product behaves as documented and intended.

- Add an automated test suite covering the fixed logic.

- Verify the release build (0 errors, 0 warnings).

- Correct installer upgrade settings; produce version 1.0.1.

- Provide UAT test cases and support the client's UAT.

### WP3 — Project documentation (PMI)

- Charter, SoW, WBS, software description, defect log, test plan and report, CR log, risk register, decision log, configuration baseline, lessons learned.

- Keep the README consistent with the behaviour of 1.0.1.

### WP4 — Configuration management

- Capture the v1.0.0 baseline (zip snapshot + SHA-256 manifest) before the first change.

- Record the 1.0.1 configuration (file hashes, build and test evidence).

- The client commits the baseline and the release to GitHub.

## 3. Deliverables

| ID | Deliverable | Acceptance criterion | Status |
| --- | --- | --- | --- |
| D1 | Knowledge base (graphify-out/) | Graph opens in a browser; report lists components and communities | Delivered |
| D2 | Findings and recommendations report | Presented to the client before changes; decisions recorded | Delivered (session record, DEC-001…DEC-009) |
| D3 | v1.0.0 baseline snapshot and hash manifest | Zip exists outside the monitored folder; hashes in doc 10 | Delivered |
| D4 | Source code 1.0.1 with defect fixes | DEF-001…DEF-017 fixed; build 0 errors/0 warnings | Delivered — pending UAT |
| D5 | Automated test suite (Tests/ServiceTrayMonitor.Tests) | All tests pass on Release | Delivered |
| D6 | Installer project 1.0.1 | Upgrades 1.0.0 in place; no .NET Framework 4.7.2 prerequisite | Release MSI built — UAT-11 pending |
| D7 | UAT test cases | UAT-01…UAT-12 defined with expected results | Delivered |
| D8 | Project documentation pack (docs/project/) | Artifacts 01–11 present and cross-referenced | Delivered (draft) |
| D9 | Updated README | Describes 1.0.1 behaviour, tests, troubleshooting | Delivered |

## 4. Exclusions (out of scope — change control required)

- New features of any kind, including the Restart action (CR-001).

- Renaming the installed product "SystemTrayMonitor" to match the app name (CR-002).

- Code signing of the executable or MSI (CR-003).

- Changing the elevation model (for example, running without administrator rights or adding a helper Windows service).

- Deployment or installation on production machines, and changes to their services, policies, or scheduled tasks.

- Renaming or moving the repository folder miautrix-ServiceTrayMonitor.

## 5. Classification rule: defect or change?

| Question | Yes → | No → |
| --- | --- | --- |
| Does the current behaviour contradict the README, the UI text, or evident design intent, or does it lose data, hang, or leak? | Defect (in SoW, WP2) | Next question |
| Does the request add, remove, or alter functionality, UI, installed footprint, or operating model? | Change request (CR log) | Clarify with the sponsor |

Borderline items resolved as defects are recorded with their rationale in the Decision Log.

## 6. Acceptance

- Defect fixes are accepted when the linked UAT cases pass on the client's test environment and the sponsor signs the test report (doc 06).

- Documentation is accepted on sponsor review of the compiled project document.

## 7. Constraints and assumptions

See Charter §7. In addition, development-time testing is non-invasive: automated tests only read service status and use a temporary configuration folder.

## 8. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor | [TBD] |  |  |
| Project manager | [TBD] |  |  |

# 03 — Work Breakdown Structure and WBS Dictionary

Status as of 2026-09-13.

1  Service Tray Monitor — Stabilisation and Documentation

├─ 1.1 Project management

│  ├─ 1.1.1 Charter and stakeholder register

│  ├─ 1.1.2 Statement of work and scope statement

│  ├─ 1.1.3 Change control process and CR log

│  ├─ 1.1.4 Risk register, decision and assumption log

│  └─ 1.1.5 Closure: lessons learned, final project document

├─ 1.2 Discovery and analysis (WP1)

│  ├─ 1.2.1 Source and installer review

│  ├─ 1.2.2 Knowledge base (graphify)

│  └─ 1.2.3 Findings and recommendations report

├─ 1.3 Configuration management (WP4)

│  ├─ 1.3.1 v1.0.0 baseline snapshot and hash manifest

│  ├─ 1.3.2 GitHub baseline commit (client)

│  └─ 1.3.3 Release 1.0.1 configuration record

├─ 1.4 Defect testing and resolution (WP2)

│  ├─ 1.4.1 Reproduction and root-cause analysis

│  ├─ 1.4.2 Defect fixes DEF-001…DEF-017

│  ├─ 1.4.3 Automated test suite

│  ├─ 1.4.4 Build verification

│  ├─ 1.4.5 Installer corrections and Release MSI build

│  └─ 1.4.6 User acceptance testing support

└─ 1.5 Documentation (WP3)

├─ 1.5.1 Software description

├─ 1.5.2 README update

├─ 1.5.3 Test plan, test report, traceability matrix

└─ 1.5.4 Compiled project document

## WBS dictionary

| WBS | Work package | Description / output | Owner | Acceptance | Status |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | Charter | Doc 01 | PM [TBD] | Sponsor signature | Draft |
| 1.1.2 | SoW | Doc 02 | PM [TBD] | Sponsor signature | Draft |
| 1.1.3 | Change control | Doc 07, CR form | PM [TBD] | Process agreed | In place |
| 1.1.4 | Risk and decision logs | Docs 08, 09 | PM [TBD] | Reviewed at status meetings | Open |
| 1.1.5 | Closure | Doc 11, compiled document | PM [TBD] | Sponsor sign-off | Not started |
| 1.2.1 | Source review | All .cs, .csproj, .sln, manifest, .vdproj | Dev team | Findings presented | Complete |
| 1.2.2 | Knowledge base | graphify-out/ (170 nodes, 293 edges, 12 communities) | Dev team | Graph renders; report generated | Complete |
| 1.2.3 | Findings report | 14 findings + decisions requested | Dev team | Client decisions received | Complete |
| 1.3.1 | v1.0.0 baseline | Zip + SHA-256 manifest (doc 10) | Dev team | Hashes recorded | Complete |
| 1.3.2 | GitHub baseline commit | Commit of v1.0.0, then 1.0.1 | Client | Commits visible in GitHub | Pending |
| 1.3.3 | 1.0.1 record | File hashes, build and test evidence | Dev team | Doc 10 complete | Complete |
| 1.4.1 | Root cause | Defect Log entries with evidence | Dev team | Each DEF has a root cause | Complete |
| 1.4.2 | Fixes | Code changes, 1.0.1 | Dev team | Build + tests pass | Complete |
| 1.4.3 | Test suite | xUnit project, 38 tests | Dev team | 100 % pass | Complete |
| 1.4.4 | Build verification | Release build 0 errors / 0 warnings | Dev team | Build log | Complete |
| 1.4.5 | Installer | .vdproj 1.0.1; Release MSI | Dev team / client | UAT-11 | Release MSI built (doc 10); UAT pending |
| 1.4.6 | UAT support | UAT-01…UAT-12 | Client testers | Signed test report | Not started |
| 1.5.1 | Software description | Doc 04 | Dev team | Reviewed | Complete |
| 1.5.2 | README | Updated README.md | Dev team | Consistent with 1.0.1 | Complete |
| 1.5.3 | Test documentation | Doc 06 | Dev team | Reviewed | Complete |
| 1.5.4 | Compiled document | ServiceTrayMonitor-Project-Document.docx (DOCX, DEC-012) | PM [TBD] | Sponsor sign-off | Draft compiled |

Change requests (CR-001…) are outside this WBS baseline. Once approved, each CR adds its own work packages under a new element 1.6 Approved changes.

# 04 — Software Description (Technical Baseline, v1.0.1)

## 1. Product overview

| Item | Value |
| --- | --- |
| Name | Service Tray Monitor (installed product name: "SystemTrayMonitor" — see CR-002) |
| Manufacturer | Miautrix |
| Version | 1.0.1 (assembly Version and MSI ProductVersion) |
| Type | Windows desktop system-tray application (WinForms) |
| Runtime | .NET 8 (net8.0-windows), x64 Desktop Runtime |
| Elevation | requireAdministrator (UAC prompt at launch) |
| Package | Visual Studio Installer Project Setup/SetupSTM → SetupSTM.msi + setup.exe bootstrapper |
| External dependency | System.ServiceProcess.ServiceController 8.0.0 |

Purpose. Administrators pick Windows services to watch. The tray icon summarises their health by colour, and the tray menu and main window start, stop, pause, and resume them.

Users. IT administrators and operators on Windows workstations or servers.

## 2. Functional summary

| Function | Where | Notes |
| --- | --- | --- |
| Tray icon with summary colour | TrayAppContext, IconFactory.SummaryColor | Red if any service is stopped or missing; amber if pending or paused; green if all running; gray if none configured |
| Tooltip | TrayAppContext.ApplyStatusesToTray | First 8 services, trimmed to the 127-character limit |
| Tray menu per service | TrayAppContext.BuildMenu | Status dot plus Start/Stop/Pause/Resume, enabled by ServiceActionRules |
| Main window grid | Forms/ManageServicesForm | Sortable; updated in place each poll (keeps selection, sort, scroll) |
| Choose monitored services | Forms/SettingsForm | Filterable checklist; poll interval 2–300 s; Start with Windows |
| Admin credential | Forms/CredentialsForm | Save / Test / Clear; blank password keeps the saved one for the same login |
| Start with Windows | Services/StartupManager | Per-user scheduled task, run level Highest, no execution time limit |
| Polling | Services/ServiceMonitorEngine | System.Timers.Timer; serialized refreshes; overlapping ticks skipped |

## 3. Architecture

Component diagram — Mermaid source (rendered graphically in the GitHub repository):

flowchart LR

Program --> TrayAppContext

TrayAppContext --> ServiceMonitorEngine

TrayAppContext --> ManageServicesForm

TrayAppContext --> SettingsForm

TrayAppContext --> CredentialsForm

TrayAppContext --> StartupManager

TrayAppContext --> IconFactory

ManageServicesForm --> ServiceMonitorEngine

SettingsForm --> ServiceMonitorEngine

ServiceMonitorEngine --> ServiceActions

ServiceMonitorEngine --> ElevatedServiceRunner

ServiceMonitorEngine --> ConfigManager

ElevatedServiceRunner --> ServiceActions

CredentialsForm --> ConfigManager

CredentialsForm --> ElevatedServiceRunner

ServiceActions --> SCM[(Windows Service Control Manager)]

ConfigManager --> CFG[(config.json in AppData)]

StartupManager --> TS[(Task Scheduler)]

### Components

| Layer | File | Responsibility |
| --- | --- | --- |
| Entry | Program.cs | STA entry point; runs TrayAppContext (no main window) |
| Shell | TrayAppContext.cs | Owns tray icon, menu, engine, and windows; installs the WinForms synchronization context; runs actions off the UI thread |
| UI | Forms/ManageServicesForm.cs | Grid of monitored services and action buttons |
| UI | Forms/SettingsForm.cs | Monitored-service selection, poll interval, Start with Windows |
| UI | Forms/CredentialsForm.cs | Admin credential entry, test, and clear |
| Model | Models/MonitoredService.cs | Live service state; AppSettings (persisted configuration) |
| Model | Models/StatusPalette.cs | Status colours (single source); ServiceActionRules (which actions are allowed) |
| Model | Models/ServiceSelection.cs | Checked-service working set independent of the filter; InstalledService record |
| Model | Models/StoredCredential.cs | Domain, username, and in-memory password |
| Service | Services/ServiceMonitorEngine.cs | Polling and status events; action entry points with the credential fallback |
| Service | Services/ServiceActions.cs | Start/Stop/Pause/Resume semantics and wait-for-state; error classification |
| Service | Services/ElevatedServiceRunner.cs | LogonUser (batch, then interactive) plus impersonation; credential test |
| Service | Services/ConfigManager.cs | config.json read/merge/write, DPAPI, corrupt-file backup, atomic save |
| Service | Services/StartupManager.cs | Scheduled-task registration and removal; legacy Run-key cleanup |
| Service | Services/IconFactory.cs | Runtime-drawn tray icons and menu dots (cached) |
| Tests | Tests/ServiceTrayMonitor.Tests/ | xUnit suite (see doc 06) |
| Installer | Setup/SetupSTM/SetupSTM.vdproj | MSI to [ProgramFiles64Folder]Miautrix\SystemTrayMonitor; bootstrapper for .NET 8 Desktop Runtime |

## 4. Key flows

### 4.1 Status polling

- The timer ticks every PollIntervalSeconds (minimum 1 s in the engine, 2 s in the UI).

- If a refresh is already running, the tick is skipped. Manual refreshes queue on the thread pool and run one at a time.

- Each monitored name is queried with ServiceController; missing services are marked Exists = false.

- StatusesUpdated fires on a thread-pool thread. The tray posts to the UI synchronization context, and the main window uses BeginInvoke.

### 4.2 Service action (Start / Stop / Pause / Resume)

- The UI disables the action controls and runs the action on a background task.

- ServiceMonitorEngine.Execute runs the ServiceActions method with the app's own elevated token.

- The action waits until the service reaches the target state (15 s timeout). Success means the state was reached. "Already running/stopped/paused" counts as success.

- If Windows returns Access is denied and a credential is saved, the same action is retried inside ElevatedServiceRunner.Run: LogonUser with a batch logon (not UAC-filtered), falling back to an interactive logon if the batch right isn't granted. The action then runs under WindowsIdentity.RunImpersonated.

- The result shows as a balloon (tray) or status line plus a message box on failure (window), and a refresh is queued.

### 4.3 Saving settings

- SettingsForm raises SettingsSaved with the general settings only.

- ConfigManager.SaveGeneralSettings re-reads the file, replaces the general fields, keeps the credential fields, and writes atomically (temp file + move).

- The engine interval and list are updated; StartupManager.Apply runs in the background.

### 4.4 Credential save and test

- Save: username and password are required. A blank password with an unchanged login reuses the saved password. Only credential fields are changed on disk.

- Test: signs in (batch, then interactive) and reports success only when the token is a full administrator token and the SCM can be opened with full access.

### 4.5 Start with Windows

- Enabled → task ServiceTrayMonitor (<user>) is registered from XML: logon trigger for that user, InteractiveToken, HighestAvailable, ExecutionTimeLimit PT0S, IgnoreNew.

- Disabled → the task is deleted if present. Both paths remove the legacy 1.0.0 HKCU\...\Run value.

- At launch, if enabled, the task is re-registered so it follows the current executable path.

## 5. Data

%AppData%\ServiceTrayMonitor\config.json (per Windows user):

| Field | Type | Default | Notes |
| --- | --- | --- | --- |
| MonitoredServiceNames | string[] | [] | Internal service names; order = display order at save |
| PollIntervalSeconds | int | 5 | UI range 2–300 |
| StartWithWindows | bool | false | Drives the scheduled task |
| CredentialDomain | string | "" | Blank = local account (.); ignored for UPN usernames |
| CredentialUsername | string | "" | Credential is "configured" when non-blank |
| CredentialEncryptedPasswordBase64 | string | "" | DPAPI CurrentUser + fixed entropy, Base64 |

An unreadable file is renamed config.json.corrupt-yyyyMMdd-HHmmss; defaults are used and a balloon warns the user.

## 6. Security model

- The process runs elevated (manifest). Service control uses that token first.

- The saved password is encrypted with DPAPI for the current Windows user. The entropy value is in the binary, so it is not a secret against other processes of the same user.

- The credential is used in-process through LogonUser and impersonation. It is never passed on a command line or to a child process (1.0.0 used sc.exe child processes).

- Least-privilege option: grant a dedicated account rights on specific services (sc sdset, see README).

- The executable and MSI are unsigned (CR-003).

- Settings, credential, and startup task belong to the elevated user. With over-the-shoulder UAC (another admin's credentials entered at the prompt), they belong to that admin (R-02).

## 7. Build, test, and packaging

| Task | Command / action |
| --- | --- |
| Build | dotnet build ServiceTrayMonitor.sln -c Release |
| Test | dotnet test Tests/ServiceTrayMonitor.Tests -c Release |
| Single-file exe | dotnet publish -c Release -r win-x64 --self-contained true -p:PublishSingleFile=true |
| MSI | Visual Studio → right-click SetupSTM → Build (Release). The setup project isn't included in the solution build configuration. |

Tooling used on 2026-09-13: .NET SDK 10.0.400 (targets net8.0), Visual Studio 18 (Community 18.9.2), xUnit 2.9.3, xunit.runner.visualstudio 4.0.0, Microsoft.NET.Test.Sdk 18.10.0.

## 8. Known limitations (1.0.1)

- No Restart action (CR-001).

- Only local-machine services.

- The credential fallback is triggered only by Access is denied; other errors are reported as-is.

- The installer product name differs from the app name (CR-002); binaries are unsigned (CR-003).

- The tooltip shows at most 8 services (Windows limit of 127 characters).

# 05 — Defect Log

Baseline: v1.0.0 (snapshot 2026-09-13). Fix release: 1.0.1. Detection methods: CR = code review, RP = reproduced, KB = knowledge-base analysis, BLD = build output. Verification references point to doc 06.

## Summary

| ID | Title | Severity | Status |
| --- | --- | --- | --- |
| DEF-001 | Saving monitored services erases the saved admin credential | High | Verified (automated) — awaiting UAT |
| DEF-002 | Filter loses checks; Save drops services hidden by the filter | High | Verified (automated) — awaiting UAT |
| DEF-003 | "Start with Windows" never starts the app | High | Verified (automated) — awaiting UAT |
| DEF-004 | Credential Test hangs the application | High | Fixed (reproduced on 1.0.0 pattern) — awaiting UAT |
| DEF-005 | A saved credential makes service actions fail with "Access is denied" | High | Fixed — awaiting UAT |
| DEF-006 | UI freezes for up to 15 s during service actions | Medium | Fixed — awaiting UAT |
| DEF-007 | Grid loses sort, scroll, and (likely) selection on every poll | Medium | Fixed — awaiting UAT |
| DEF-008 | Action results differ between the direct and credential paths | Medium | Fixed — awaiting UAT |
| DEF-009 | Overlapping polls, blocking cross-thread Invoke, shared list reference | Medium | Verified (automated) — awaiting UAT |
| DEF-010 | Corrupt config.json silently replaced; non-atomic writes | Medium | Verified (automated) — awaiting UAT |
| DEF-011 | Resource leaks (menu items, event handlers, service handles) | Low | Fixed — awaiting UAT |
| DEF-012 | Missing services shown red instead of gray; duplicated colour/rule logic | Low | Verified (automated) — awaiting UAT |
| DEF-013 | Installer cannot upgrade; unneeded .NET Framework 4.7.2 prerequisite | Medium | Fixed — Release MSI built — awaiting UAT |
| DEF-014 | Build warning WFAC010 (DPI settings in manifest) | Low | Verified (build) |
| DEF-015 | Tray updates run on thread-pool threads instead of the UI thread | Medium | Fixed — awaiting UAT |
| DEF-016 | Cancel keeps unsaved checks; poll interval > 300 in config crashes the window | Low | Fixed — awaiting UAT |
| DEF-017 | Re-saving the credential without retyping the password stores an empty password | Medium | Fixed — awaiting UAT |

Totals: 17 defects — High 5, Medium 8, Low 4. All fixed in 1.0.1; none closed until UAT is accepted.

### DEF-001 — Saving monitored services erases the saved admin credential

- Severity / priority: High / P1 — data loss. Detected: 2026-09-13, CR.

- Component: TrayAppContext.cs, Services/ConfigManager.cs.

- Steps (1.0.0): Launch → Admin Credentials → Save an account → Manage Monitored Services → Save.

- Expected: The credential stays saved. Actual: The credential fields revert to their values at app start (empty on a fresh setup).

- Root cause: TrayAppContext loaded AppSettings once at startup. The credential was saved separately (load → modify → save), but saving settings serialised the stale startup object over the file.

- Resolution: ConfigManager.SaveGeneralSettings re-reads the file and replaces only the general fields. Credential saves change only credential fields. All writes are serialised by a lock.

- Verification: AT-03 SaveGeneralSettings_KeepsCredentialSavedSinceStartup, ClearCredential_KeepsGeneralSettings; UAT-05.

### DEF-002 — Filter loses checks; Save drops services hidden by the filter

- Severity / priority: High / P1 — monitored services silently removed. Detected: CR.

- Component: Forms/SettingsForm.cs.

- Steps (1.0.0): Monitor A and B → open Manage Monitored Services → type a filter that shows only A → Save.

- Expected: A and B stay monitored. Actual: Only A is saved. Checks made before changing the filter are also lost.

- Root cause: The list was rebuilt from saved settings on every keystroke, and Save read only the CheckedItems currently visible.

- Resolution: A new ServiceSelection working set records every check/uncheck and is saved regardless of the filter. Names that aren't installed are preserved.

- Verification: AT-02 (9 tests); UAT-04.

### DEF-003 — "Start with Windows" never starts the app

- Severity / priority: High / P1 — documented feature non-functional. Detected: CR; the reference server has StartWithWindows = true with the Run-key entry present.

- Component: Services/ConfigManager.cs (1.0.0 ApplyStartupSetting).

- Root cause: The app requires elevation, and Windows does not launch elevated programs from HKCU\Software\Microsoft\Windows\CurrentVersion\Run at logon.

- Resolution: StartupManager registers a per-user scheduled task (logon trigger, highest privileges, no 72-hour limit, IgnoreNew). The legacy Run value is removed automatically. Failures are reported in a balloon.

- Verification: AT-04 (task XML content and escaping); UAT-09.

### DEF-004 — Credential Test hangs the application

- Severity / priority: High / P1 — application hang. Detected: CR; reproduced 2026-09-13 (RP-01).

- Component: Services/ElevatedServiceRunner.cs (1.0.0 TestCredential).

- Root cause: sc.exe query state= all ran with stdout redirected but never read, while stderr was read to the end first. The output (~94 KB on the reference server) filled the pipe buffer, so sc.exe blocked, stderr never closed, and the UI thread waited forever. The 1.0.0 RunAction read before WaitForExit, so its 15 s timeout was ineffective too.

- Resolution: sc.exe removed. The test signs in with LogonUser and checks the token and SCM access in-process, off the UI thread.

- Verification: RP-01 (defect evidence on the 1.0.0 pattern); AT-05 CredentialRunner_WithoutCredential_FailsCleanly; UAT-06.

### DEF-005 — A saved credential makes service actions fail with "Access is denied"

- Severity / priority: High / P1 — the core function fails in the configured scenario. Detected: CR/KB.

- Component: Services/ServiceMonitorEngine.cs, Services/ElevatedServiceRunner.cs.

- Root cause: Once a credential was saved, every action went through sc.exe launched with alternate credentials. That uses an interactive-type logon, and UAC filters it to a non-admin token. The app was already elevated, so actions that would have succeeded with its own token failed.

- Resolution (DEC-002): Actions run with the app's own elevated token first. Only on Access is denied are they retried as the saved account, using LogonUser batch logon (full token) plus impersonation, falling back to interactive logon. Messages explain filtered-token outcomes.

- Verification: AT-05; UAT-06, UAT-07. Real alternate-account verification is pending (R-01).

### DEF-006 — UI freezes for up to 15 s during service actions

- Severity: Medium. Detected: CR. Component: TrayAppContext.cs, Forms/ManageServicesForm.cs.

- Root cause: Actions (including WaitForStatus up to 15 s) ran synchronously on the UI thread.

- Resolution: Actions run on Task.Run. The window shows "Starting…" and disables action buttons while an action runs.

- Verification: UAT-02.

### DEF-007 — Grid loses sort, scroll, and (likely) selection on every poll

- Severity: Medium. Detected: CR. Component: Forms/ManageServicesForm.cs.

- Root cause: Every poll cleared and re-added all rows. Selection was restored with Row.Selected, but actions read CurrentRow, which moves to the first row after a rebuild. The highlight and the action target could differ (by inspection; not reproduced).

- Resolution: Rows are updated in place when the service set is unchanged. On a rebuild, sort, current cell, and scroll are restored.

- Verification: UAT-03.

### DEF-008 — Action results differ between the direct and credential paths

- Severity: Medium. Detected: CR. Component: ElevatedServiceRunner.cs (1.0.0), ServiceMonitorEngine.cs.

- Root cause: The sc.exe path reported success when the request was accepted (pending), and reported "already running" as a failure. The direct path waited and treated "already" as success.

- Resolution: Both paths use ServiceActions: they wait for the target state, handle pending states, and give a clear message for Start on a paused service.

- Verification: AT-05; UAT-02, UAT-07.

### DEF-009 — Overlapping polls, blocking cross-thread Invoke, shared list reference

- Severity: Medium. Detected: CR. Component: ServiceMonitorEngine.cs, ManageServicesForm.cs.

- Root cause: Timer and UI both called RefreshNow with no guard, so slow SCM queries could overlap. The window used synchronous Invoke from the timer thread. The engine held the caller's list instance.

- Resolution: Refreshes are serialised, and overlapping timer ticks are skipped. BeginInvoke is used with disposal guards, and the engine copies the list.

- Verification: AT-06 UpdateMonitoredList_CopiesTheCallersList, Refresh_ReportsExistingAndMissingServices; UAT-12.

### DEF-010 — Corrupt config.json silently replaced; non-atomic writes

- Severity: Medium. Detected: CR. Component: Services/ConfigManager.cs.

- Root cause: Parse errors were swallowed, and defaults were written over the file at the next save. Writes were in place.

- Resolution: The corrupt file is renamed config.json.corrupt-<timestamp> and a balloon warns. Saves refuse to overwrite a file that is locked or unreadable for I/O reasons. Writes go to a temp file that is then moved into place.

- Verification: AT-03 CorruptConfig_IsBackedUp_AndDefaultsReturned, Save_LeavesNoTempFileBehind; UAT-10.

### DEF-011 — Resource leaks

- Severity: Low. Detected: CR/KB.

- Root cause:

  - A new Format handler was attached on every filter keystroke.

  - Menu items and a bold Font were recreated on every menu open without disposal.

  - ServiceController objects from GetServices were never disposed.

  - The main window never unsubscribed from engine events.

- Resolution:

  - The handler is attached once.

  - Menu items are disposed, with the cached images detached first; the font is created once.

  - Controllers are disposed after reading names.

  - The window unsubscribes on dispose.

- Verification: UAT-12 (long-running observation).

### DEF-012 — Missing services shown red instead of gray; duplicated colour and rule logic

- Severity: Low. Detected: KB (duplicated logic) / CR. Component: Models/MonitoredService.cs, Services/IconFactory.cs, forms.

- Root cause: StatusColor ignored Exists, so a missing service kept the default Stopped colour. The README documents ⚪. Colours were defined twice, and action enable rules were duplicated in two UIs.

- Resolution: StatusPalette is the single source of colours (gray when missing). ServiceActionRules is shared by the menu and the window.

- Verification: AT-01 (15 tests); UAT-01.

### DEF-013 — Installer cannot upgrade; unneeded prerequisite

- Severity: Medium. Detected: CR. Component: Setup/SetupSTM/SetupSTM.vdproj.

- Root cause: RemovePreviousVersions = FALSE with a fixed ProductVersion 1.0.0 means a new build would install side by side or be blocked. The bootstrapper listed .NET Framework 4.7.2, which a .NET 8 app doesn't use.

- Resolution: ProductVersion 1.0.1, new ProductCode and PackageCode, same UpgradeCode, RemovePreviousVersions = TRUE, .NET Framework 4.7.2 prerequisite removed. The .NET 8 Desktop Runtime prerequisite is kept.

- Verification: Release MSI built 2026-09-13; MSI properties checked (doc 10); UAT-11.

### DEF-014 — Build warning WFAC010

- Severity: Low. Detected: BLD. Component: app.manifest, ServiceTrayMonitor.csproj.

- Resolution: DPI settings were moved from the manifest to <ApplicationHighDpiMode>PerMonitorV2.

- Verification: BV-01 (Release build, 0 warnings).

### DEF-015 — Tray updates run on thread-pool threads

- Severity: Medium — cross-thread UI access, intermittent faults. Detected: 2026-09-13 during DEF-006 fix, CR.

- Component: TrayAppContext.cs.

- Root cause: SynchronizationContext.Current was captured in the constructor before any control existed, so it was null. The fallback new SynchronizationContext() posts to the thread pool.

- Resolution: A WindowsFormsSynchronizationContext is installed explicitly before it is captured.

- Verification: UAT-01, UAT-12.

### DEF-016 — Cancel keeps unsaved checks; out-of-range interval crashes the window

- Severity: Low. Detected: CR. Component: Forms/SettingsForm.cs, TrayAppContext.cs.

- Root cause: The hidden form kept its state between openings. NumericUpDown.Value was set to max(2, value) without an upper bound (300), so a value over 300 threw.

- Resolution: The window resets from saved settings each time it opens (unless already open), and the interval is clamped to 2–300.

- Verification: UAT-04.

### DEF-017 — Re-saving the credential without retyping the password stores an empty password

- Severity: Medium — silently breaks the credential. Detected: 2026-09-13 during DEF-001 fix, CR.

- Component: Forms/CredentialsForm.cs.

- Root cause: The form never re-displays the password, but Save encrypted whatever was in the empty password box.

- Resolution: A blank password with an unchanged login keeps the saved password (placeholder text explains this). A different login requires a password.

- Verification: UAT-08.

# 06 — Test Plan, Test Report, and Requirements Traceability Matrix

| Field | Value |
| --- | --- |
| Release under test | 1.0.1 (defect-fix release) |
| Baseline for comparison | 1.0.0 |
| Report date | 2026-09-13 |
| Document version | 0.1 |

## 1. Test strategy

| Level | Purpose | Technique | Where |
| --- | --- | --- | --- |
| Reproduction (RP) | Confirm a defect exists before fixing | Run the defective pattern in isolation | Developer machine |
| Unit (AT) | Pure logic: colours, action rules, selection, error classification | xUnit | Tests/ServiceTrayMonitor.Tests |
| Component (AT) | ConfigManager against a temporary folder; StartupManager task XML | xUnit | same |
| Integration, read-only (AT) | ServiceMonitorEngine against the local Service Control Manager | xUnit, queries only | same |
| Build verification (BV) | Compile Release with no warnings | dotnet build | Developer machine |
| User acceptance (UAT) | End-to-end behaviour, elevation, credentials, installer, startup | Manual test cases below | Client test machine |

Non-invasive rule (constraint C3): automated tests never start, stop, or reconfigure services, never register scheduled tasks, and never touch the user's real config.json. Everything that changes machine state is covered by UAT on a test machine.

Entry criteria (UAT): 1.0.1 build and MSI available; a test machine with 1.0.0 installed; accounts for UAT-06/07 (local admin, domain admin, non-admin with a per-service ACL); a non-critical test service.

Exit criteria: all AT pass; BV clean; UAT-01…UAT-12 pass, or failures are logged as new DEF entries and either fixed or accepted by the sponsor; sign-off in §7.

## 2. Test environment (development verification)

| Item | Value |
| --- | --- |
| OS | Windows Server 2025 Datacenter 10.0.26100 |
| Account | Domain administrator, process elevated |
| .NET SDK | 10.0.400 (target framework net8.0-windows); 8.0.420 also installed |
| Visual Studio | 18 Community (18.9.2) |
| Test packages | xunit 2.9.3, xunit.runner.visualstudio 4.0.0, Microsoft.NET.Test.Sdk 18.10.0 |

## 3. Results — reproduction and build

| ID | Description | Result | Evidence |
| --- | --- | --- | --- |
| RP-01 | 1.0.0 TestCredential pattern: sc.exe query state= all with stdout redirected but unread, stderr read first | Defect reproduced. The stderr read didn't finish within 10 s and sc.exe hadn't exited. After draining stdout the process exited with code 0, having produced 94,479 characters. | Session log 2026-09-13 (DEF-004) |
| BV-00 | 1.0.0 Debug build (before changes) | 0 errors, 1 warning (WFAC010) | Session log 2026-09-13 |
| BV-01 | 1.0.1 dotnet build ServiceTrayMonitor.sln -c Release | Pass — 0 errors, 0 warnings | Session log 2026-09-13 (DEF-014) |

## 4. Results — automated tests

Command: dotnet test Tests/ServiceTrayMonitor.Tests -c Release Summary: Passed 38, Failed 0, Skipped 0, Total 38 (duration 88 ms).

| Group | Test class | Tests | Covers | Result |
| --- | --- | --- | --- | --- |
| AT-01 | StatusAndRulesTests | 15 (palette theory ×5; not-found colour; summary colour ×4; action rules ×5) | DEF-012 | 15/15 pass |
| AT-02 | ServiceSelectionTests | 9 (checks kept across filter; not-installed kept; case-insensitive uncheck; order; filter theory ×5) | DEF-002 | 9/9 pass |
| AT-03 | ConfigManagerTests | 5 (credential kept on general save; clear keeps settings; password not plain text; corrupt file backed up; no temp file left) | DEF-001, DEF-010 | 5/5 pass |
| AT-04 | StartupManagerTests | 2 (logon/elevated/no-limit XML; XML escaping) | DEF-003 | 2/2 pass |
| AT-05 | ServiceActionsTests | 4 (access-denied detection ×2; Win32 reason in message; runner without credential) | DEF-004, DEF-005, DEF-008 | 4/4 pass |
| AT-06 | ServiceMonitorEngineTests | 3 (existing vs. missing service; list copied; installed list sorted) | DEF-009 | 3/3 pass |

## 5. User acceptance test cases

Use a test machine. "Test service" = a non-critical service. For pause cases, pick one where (Get-Service <name>).CanPauseAndContinue is True.

| ID | Title | Preconditions | Steps | Expected result | Covers | Result |
| --- | --- | --- | --- | --- | --- | --- |
| UAT-01 | Tray status and colours | App running; monitor one running, one stopped, and one name that doesn't exist (edit config) | 1. Hover the tray icon. 2. Open the tray menu. | Icon is red. Menu dots: green (running), red (stopped), gray (not found, "[Not found]"). Tooltip lists the services. No errors. | DEF-012, DEF-015 | Not run |
| UAT-02 | Actions from tray and window; responsiveness | Test service stopped | 1. Tray → service → Start. 2. While it starts, open the tray menu and move the main window. 3. Main window → Stop. 4. Pause then Resume (pausable service). 5. Start a paused service from the tray. | Each action shows success only after the target state is reached. UI stays responsive, and buttons show "Starting…" and are disabled while running. Step 5 shows "The service is paused. Use Resume instead." | DEF-006, DEF-008 | Not run |
| UAT-03 | Grid keeps selection, sort, scroll | Monitor ≥ 15 services; poll interval 2 s | 1. Sort by Status. 2. Scroll down and select a row near the bottom. 3. Wait 20 s. 4. Click Stop on the selected (test) service. | Sort, scroll position, and selection stay put across polls. Stop acts on the highlighted service. | DEF-007 | Not run |
| UAT-04 | Service selection, filter, and Cancel | Monitoring A and B | 1. Manage Monitored Services. 2. Filter to show only A; check C (visible via filter). 3. Clear the filter; confirm A, B, C are checked. 4. Filter to A only; Save. 5. Reopen; uncheck B; Cancel; reopen. 6. Set PollIntervalSeconds to 999 in config, restart, open the window. | Step 3: all three checked. Step 4: A, B, C monitored. Step 5: B still checked (Cancel discarded). Step 6: the window opens with 300. | DEF-002, DEF-016 | Not run |
| UAT-05 | Credential survives settings save | No credential saved | 1. Admin Credentials → enter a valid account → Save. 2. Manage Monitored Services → change the interval → Save. 3. Reopen Admin Credentials. | Status shows "Currently configured: DOMAIN\user". config.json still holds username and encrypted password. | DEF-001 | Not run |
| UAT-06 | Credential Test | Accounts: (a) local admin, (b) domain admin, (c) wrong password, (d) standard user | Admin Credentials → enter each → Test | (a)/(b): "Credential works … full administrator token" within a few seconds; UI never hangs. (c): "Sign-in failed … user name or password is incorrect". (d): "Signed in … without a full administrator token". | DEF-004, DEF-005 | Not run |
| UAT-07 | Fallback to the saved credential | Test service whose DACL denies the operator's admin group but grants the saved account (sc sdset); credential saved | 1. Start the test service from the tray. 2. Clear the credential and repeat. | Step 1: succeeds (the retry as the saved account runs automatically). Step 2: fails with "Access is denied. Save an account with rights…". | DEF-005, DEF-008 | Not run |
| UAT-08 | Re-save the credential without retyping the password | Credential saved | 1. Admin Credentials → leave the password blank → Save. 2. Test. 3. Change the username, leave the password blank → Save. | Step 1 saves; step 2 still says "Credential works". Step 3 asks for the password. | DEF-017 | Not run |
| UAT-09 | Start with Windows | App 1.0.1 installed; legacy Run value present from 1.0.0 (optional) | 1. Enable Start with Windows → Save. 2. schtasks /Query /TN "ServiceTrayMonitor (<user>)" /XML. 3. Sign out and back in. 4. Disable → Save → query again. | Step 2: task exists with HighestAvailable and PT0S; the Run value is gone. Step 3: the app starts at logon, elevated, with no UAC prompt. Step 4: the task no longer exists. | DEF-003 | Not run |
| UAT-10 | Corrupt configuration | App closed | 1. Replace config.json with { broken. 2. Start the app. | A balloon reports the reset. config.json.corrupt-<timestamp> holds the broken content, and the app runs with defaults. | DEF-010 | Not run |
| UAT-11 | Installer upgrade | Test machine with SystemTrayMonitor 1.0.0 installed | 1. Run the 1.0.1 setup.exe. 2. Open Apps & Features. 3. Launch the app. | No .NET Framework 4.7.2 prompt. A single "SystemTrayMonitor" entry, version 1.0.1. The app starts, and the existing config and credential are kept. | DEF-013 | Not run |
| UAT-12 | Long run and exit | Monitor 10 services; poll 2 s | 1. Leave running 8 h, opening the tray menu and the windows periodically. 2. Exit from the tray. | Handle and memory counts (Task Manager: GDI/USER objects) stay flat. No error dialogs. Exit removes the icon and ends the process. | DEF-009, DEF-011, DEF-015 | Not run |

## 6. Requirements traceability matrix

| Req. | Requirement | Source | Defects / CRs | Automated tests | UAT |
| --- | --- | --- | --- | --- | --- |
| REQ-01 | Show service status with colour coding (tray icon, menu, grid) | README | DEF-012, DEF-015 | AT-01, AT-06 | UAT-01 |
| REQ-02 | Start, Stop, Pause, Resume from tray and main window | README | DEF-006, DEF-008; CR-001 (Restart) | AT-05 | UAT-02 |
| REQ-03 | Choose monitored services with a filterable list | README | DEF-002, DEF-016 | AT-02 | UAT-04 |
| REQ-04 | Sortable grid view | README | DEF-007 | — | UAT-03 |
| REQ-05 | Configurable poll interval | README | DEF-009, DEF-016 | AT-06 | UAT-04, UAT-12 |
| REQ-06 | Start with Windows | README | DEF-003 | AT-04 | UAT-09 |
| REQ-07 | Store admin credential with a DPAPI-encrypted password | README, DEC-002 | DEF-001, DEF-017 | AT-03 | UAT-05, UAT-08 |
| REQ-08 | Service actions succeed using the saved credential when needed | Client 2026-09-13, DEC-002 | DEF-004, DEF-005 | AT-05 | UAT-06, UAT-07 |
| REQ-09 | Settings persist safely in %AppData% | README | DEF-001, DEF-010 | AT-03 | UAT-10 |
| REQ-10 | Installable and upgradable via MSI | Installer project | DEF-013; CR-002, CR-003 | — | UAT-11 |
| REQ-11 | Stable long-running tray process | Implied | DEF-009, DEF-011, DEF-015 | AT-06 | UAT-12 |
| REQ-12 | Clean build | Quality | DEF-014 | BV-01 | — |

## 7. Sign-off

| Role | Name | Result (Accept / Accept with conditions / Reject) | Signature | Date |
| --- | --- | --- | --- | --- |
| Client test lead | [TBD] |  |  |  |
| Sponsor | [TBD] |  |  |  |

# 07 — Change Request Log

Integrated change control (PMI): every change to scope, functionality, installed footprint, or operating model is submitted as a CR, analysed for impact, and decided by the sponsor (or change control board) before implementation. Defect fixes that restore intended behaviour are not CRs (see SoW §5).

## Process

- Submit — anyone fills in the CR form below and adds a row to the log.

- Analyse — the dev team estimates impact on scope, schedule, cost, quality, and risk, and lists affected components and tests.

- Decide — the sponsor approves, rejects, or defers the CR. The decision is recorded in the log and in doc 09.

- Plan — approved CRs get WBS elements under 1.6 Approved changes, acceptance criteria, and UAT cases.

- Implement and verify — code, tests, and documentation are updated; the release is recorded in doc 10.

- Close — the CR is accepted in UAT and the log is updated.

## Log

| ID | Title | Requested by | Date | Type | Priority | Impact (summary) | Status | Decision / date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CR-001 | Add Restart action for monitored services | Client | 2026-09-13 | New functionality | [TBD] | Engine action (stop → wait → start, dependent services), tray menu, main window, rules, tests, README | Submitted | — |
| CR-002 | Align installed product name "SystemTrayMonitor" with "Service Tray Monitor" | Dev team (analysis) | 2026-09-13 | Installer / branding | Low | .vdproj ProductName and Title, Start-menu entry, install folder; upgrade path must be tested | Submitted | — |
| CR-003 | Code-sign the executable and MSI | Dev team (analysis) | 2026-09-13 | Release / security | Medium | Certificate procurement, signing step, timestamp server; removes "unknown publisher" at UAC and SmartScreen | Submitted | — |

New features to be discussed after the defect-fix tasks will be added here as CR-004 onward.

## CR form (template)

| Field | Entry |
| --- | --- |
| CR ID | CR-nnn |
| Title |  |
| Requested by / date |  |
| Description of change |  |
| Business justification |  |
| Type | New functionality / Change to existing functionality / Installer / Documentation / Other |
| Priority | Critical / High / Medium / Low |
| Affected components |  |
| Impact — scope |  |
| Impact — schedule |  |
| Impact — cost / effort |  |
| Impact — quality / testing | New or changed AT and UAT cases |
| Impact — risk | New or changed risk IDs |
| Acceptance criteria | WHEN … THE SYSTEM SHALL … |
| Alternatives considered |  |
| Decision | Approved / Rejected / Deferred |
| Decided by / date |  |
| Target release |  |
| Implementation reference | Commit / release |
| Closure date |  |

## CR-001 — Restart action (initial record)

| Field | Entry |
| --- | --- |
| Description | Add a Restart command for each monitored service in the tray menu and main window. |
| Justification | The client needs to be sure the app can start, stop, and restart services (2026-09-13). 1.0.1 has Start/Stop/Pause/Resume only. |
| Affected components | ServiceActions, ServiceMonitorEngine, ServiceActionRules, TrayAppContext, ManageServicesForm, tests, README |
| Open questions | Behaviour for services with dependents (stop dependents and restart them?); Restart on a stopped service (just start?); single timeout or per-phase timeouts |
| Proposed acceptance criteria | WHEN the user chooses Restart on a running service THE SYSTEM SHALL stop it, wait for Stopped, start it, wait for Running, and report success only when Running is reached. WHEN the app's own token is denied THE SYSTEM SHALL retry both phases as the saved admin credential. |
| Status | Submitted — analysis to be done in the feature planning session |

# 08 — Risk Register

Scale: Probability (P) and Impact (I) 1 (low) – 5 (high); Score = P × I. Response strategies per PMI: avoid, mitigate, transfer, accept, escalate.

| ID | Risk (cause → event → effect) | Category | P | I | Score | Response | Actions | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | The credential fallback (LogonUser batch + impersonation) couldn't be exercised with a real alternate admin account during development → it may behave differently on target machines → service actions could still fail when the app's own token is denied | Technical / quality | 3 | 4 | 12 | Mitigate | Run UAT-06 and UAT-07 with (a) a local admin, (b) a domain admin, (c) a non-admin with a per-service ACL. The Test button reports the token type. | Dev team + client tester | Open |
| R-02 | Operator enters another admin's credentials at the UAC prompt → the process runs as that admin → config, DPAPI credential, and startup task belong to that admin → settings appear missing or the credential can't be decrypted | Operational | 2 | 3 | 6 | Mitigate | Document in README/user guide: run the app as the same admin user who configures it. Consider a CR if shared-machine usage is required. | PM | Open |
| R-03 | Group Policy removes "Log on as a batch job" from the saved account → fallback uses an interactive, UAC-filtered token → Access is denied | Environment | 2 | 4 | 8 | Mitigate | Test button flags a non-full token. Grant the right, use the built-in Administrator, or apply per-service ACLs. Infrastructure owner to confirm the policy. | Security / infra owner | Open |
| R-04 | Policy blocks scheduled-task creation or schtasks is unavailable → Start with Windows fails | Environment | 2 | 2 | 4 | Accept / monitor | Failure is shown as a balloon; covered by UAT-09 | Client tester | Open |
| R-05 | No GitHub commit of the v1.0.0 baseline before changes → history can't show the original state → harder audit and rollback | Configuration management | 3 | 3 | 9 | Mitigate | Zip snapshot + SHA-256 manifest captured (doc 10). Client commits the baseline from the zip first, then 1.0.1. | Client | Mitigating |
| R-06 | Hand-edited .vdproj codes (ProductCode/PackageCode) or build setup cause upgrade issues → two entries in Apps & Features or blocked install | Release | 2 | 3 | 6 | Mitigate | Build the MSI in Visual Studio and run UAT-11 (upgrade from 1.0.0) on a test machine before release | Dev team / client | Open |
| R-07 | Unsigned binaries → SmartScreen / "unknown publisher" warnings → user distrust or blocked installs | Security / adoption | 3 | 2 | 6 | Transfer via CR | CR-003 (code signing) | Sponsor | Open |
| R-08 | The reference server has 1.0.0 with Start with Windows on → first 1.0.1 launch registers a task and deletes the legacy Run value → an unexpected change is noticed by admins | Operational | 4 | 1 | 4 | Accept | Communicate in release notes; expected behaviour (DEF-003 fix) | PM | Open |
| R-09 | Single reviewer (AI-assisted) analysis → defects missed or misjudged | Quality | 2 | 3 | 6 | Mitigate | Peer review of the 1.0.1 diff in GitHub; UAT; defect log open for new entries | PM | Open |
| R-10 | Behaviour change: actions now try the app's own token before the saved account (DEC-002) → audit trails show the operator's account instead of the service account | Compliance | 2 | 2 | 4 | Accept / escalate if audit requires | Confirm with the sponsor. If actions must always run as the service account, raise a CR. | Sponsor | Open |
| R-11 | Feature requests arrive during UAT → scope creep into the fix release | Scope | 3 | 3 | 9 | Avoid | Enforce change control (doc 07); features go to CRs after 1.0.1 acceptance | PM | Open |

# 09 — Decision and Assumption Log

| ID | Date | Decision | Rationale | Alternatives considered | Made by | Status |
| --- | --- | --- | --- | --- | --- | --- |
| DEC-001 | 2026-09-13 | Version control is GitHub. The GitHub app monitors the folder miautrix-ServiceTrayMonitor; the folder isn't renamed or moved, and no local git init is done by the dev team. | Client's tooling | Local git repository | Client | Confirmed |
| DEC-002 | 2026-09-13 | Keep the Admin Credentials feature. Service actions use the app's own elevated token first. On Access is denied they are retried as the saved account via LogonUser (batch, then interactive) plus impersonation. sc.exe is no longer used. | The client must be sure the app can start/stop/restart services. Own-token-first succeeds whenever the elevated app has rights; the fallback covers restricted services. Batch logon avoids UAC token filtering. In-process impersonation removes the pipe deadlock (DEF-004) and the password-to-child-process exposure. | (A) Remove credentials and rely on elevation; (B) run as a normal user and always use credentials; (C) helper Windows service running as LocalSystem | Client (keep credentials); dev team (mechanism) | Confirmed — mechanism pending UAT (R-01); audit implication R-10 |
| DEC-003 | 2026-09-13 | Keep the requireAdministrator manifest. | Needed for own-token-first control; changing the elevation model is a change, not a fix | asInvoker + credentials; helper service | Dev team (within fix scope) | Confirmed |
| DEC-004 | 2026-09-13 | Implement Start with Windows as a per-user scheduled task (logon trigger, HighestAvailable, no execution time limit); remove the legacy Run entry automatically. | The only supported way to auto-start an elevated app at logon without a UAC prompt | Run key (doesn't work elevated); Startup folder (same limitation); Windows service (different model) | Dev team | Confirmed — pending UAT-09 |
| DEC-005 | 2026-09-13 | The defect-fix release is 1.0.1: assembly Version 1.0.1; MSI ProductVersion 1.0.1 with new ProductCode/PackageCode, same UpgradeCode, RemovePreviousVersions = TRUE. | Enables in-place upgrade from 1.0.0 | Keep 1.0.0 (can't upgrade) | Dev team | Confirmed |
| DEC-006 | 2026-09-13 | Project governance: SoW = session work (analysis, KB, testing/solving, documentation). Defect fixes are part of the SoW; changes are CRs; PMI guidelines apply. | Client instruction | — | Client | Confirmed |
| DEC-007 | 2026-09-13 | Test stack: xUnit 2.9.3, xunit.runner.visualstudio 4.0.0, Microsoft.NET.Test.Sdk 18.10.0. Tests are non-invasive (temporary config folder; read-only SCM queries). | Latest stable at the time; safe to run on admin workstations | MSTest, NUnit | Dev team | Confirmed |
| DEC-008 | 2026-09-13 | Product-name alignment, code signing, and the Restart action are not part of the fix release; they are raised as CR-002, CR-003, and CR-001. | They change functionality, footprint, or process | Include in 1.0.1 | Dev team per DEC-006 | Confirmed |
| DEC-009 | 2026-09-13 | Feature discussion starts after the defect-fix tasks are complete. | Client instruction | — | Client | Confirmed |
| DEC-010 | 2026-09-13 | The v1.0.0 baseline snapshot is stored outside the monitored folder, in ..\miautrix-ServiceTrayMonitor-baseline\. | Avoid committing binaries to the repository; keep the monitored folder unchanged | Inside docs/ | Dev team | Confirmed |
| DEC-011 | 2026-09-13 | Behaviour refinements made as part of fixes: Start on a paused service returns "use Resume" (1.0.0 threw a raw error); saving a credential requires a password unless the login is unchanged; the monitored-services window resets on reopen. | They make documented behaviour work and don't add functionality (SoW §5) | Log as CRs | Dev team | Proposed — sponsor to confirm at UAT |
| DEC-012 | 2026-09-13 | Every project document deliverable is issued as DOCX. The Markdown files in docs/project/ are the source; the compiled document is docs/project/ServiceTrayMonitor-Project-Document.docx. | Client instruction ("Always DOCX") | PDF | Client | Confirmed |
| DEC-013 | 2026-09-13 | CR numbers from CR-004 onward are reserved for the new features the client will describe; none is assigned until a feature is submitted. | Keep the CR log to real requests only | Pre-register placeholder CRs | Dev team | Confirmed |

## Assumptions

| ID | Assumption | Validation | Status |
| --- | --- | --- | --- |
| A1 | Targets have the .NET 8 Desktop Runtime x64 (bootstrapper installs it if missing) | UAT-11 on a clean machine | Open |
| A2 | Operators launch the app elevated as their own admin account | R-02 | Open |
| A3 | Saved admin accounts hold "Log on as a batch job" (Administrators do by default) | UAT-06 on domain machines; R-03 | Open |
| A4 | Test accounts and a test machine are available for UAT | PM to arrange | Open |
| A5 | The EventLog service exists on every build/test machine (used by read-only tests) | Always present on Windows | Validated |

# 10 — Configuration Baseline and Release Record

## 1. Baseline v1.0.0 (as found, before any change)

| Item | Value |
| --- | --- |
| Captured | 2026-09-13, before the first modification |
| Snapshot | ..\miautrix-ServiceTrayMonitor-baseline\ServiceTrayMonitor-v1.0.0-baseline-2026-09-13.zip (outside the monitored folder, DEC-010) |
| Snapshot size | 2,731,810 bytes |
| Snapshot SHA-256 | F9F3323983357B11275491A3F2F3086F6CA3D7498B67565971D0F00EDBEFA49F |
| Contents | All project files, excluding bin/, obj/, .vs/ (build output and IDE state) |
| Build status | Debug build: 0 errors, 1 warning (WFAC010) |
| Installed on reference server | SystemTrayMonitor 1.0.0 |

### v1.0.0 file manifest (SHA-256)

| File | Bytes | SHA-256 |
| --- | --- | --- |
| app.manifest | 1467 | 1010F11E9488FB9C4FE193D718A5353DFA6C39C84CAE21DBC9093752AB60890A |
| process_monitor_icon.ico | 96887 | 7FA3DAD29CA3CCD02D03434CD3E57062051A8928E91C6F8B582CC3B47DA3C6E4 |
| process_monitor_icon_preview_128.png | 21917 | 7198C746C4503BABAEED56D0DD38CAB965C479B2A9139DEA682DBD522EDABF2A |
| Program.cs | 308 | 3D0FD5A2D890CF28C62280D3C54EADDAF1D5BA7E627EBD2CC8FF363664717860 |
| README.md | 4719 | DA546F587D319568A2F99703F361CD1CEF7DB8508748BA0E81AF5FD8433F71F4 |
| ServiceTrayMonitor.csproj | 1200 | 70224760857BBF5C63082AE3A37AFD98448241BBF5D89626B8700B01E6075682 |
| ServiceTrayMonitor.csproj.user | 487 | 2953576DE197F8DCF9DC6B346F98B3B899B77D5C792A511BB7792DF9456D0024 |
| ServiceTrayMonitor.sln | 1449 | 40218F8559077745F2AD71E0D5EBE77DF07862BABB337F310B9DD9D8E82AE101 |
| TrayAppContext.cs | 8036 | 511E76B5FF2E25DD97087ED9D4AAD18439EAB6A076FD5EF28F0B15C672B17830 |
| Forms\CredentialsForm.cs | 6172 | 2384BE1EA3FAE7FA6DE68CC5A3A3DEE36FD31FAF8EDD37B4329367B733B951AC |
| Forms\ManageServicesForm.cs | 7168 | DEA58824E35DC89F7307FAA7274F19C8BA139EC3B6DF332BBCDAD2FA0FC0EF38 |
| Forms\SettingsForm.cs | 6408 | 7630BC53106488431285798028A6AF4A75952652D65A01D3399E1E590689907E |
| Models\MonitoredService.cs | 2367 | 8FDC93A7DD949043981E6E6821F6CB91421F3EDDB05C5942F0FEE72CBE478FBB |
| Models\StoredCredential.cs | 801 | C28EAB64F8A31C4D279B9C458EA064DA646D42B5E94B2ADF44670D444B795FC7 |
| Services\ConfigManager.cs | 5733 | D65420960DAA1450CA4FD55B710C301CE0DB56852EE7BF4CF43DE9267126FC6B |
| Services\ElevatedServiceRunner.cs | 6511 | BBA29B96DF6B063F3759251D8614FB4F8E409D042FDB3E5D99EBD0152037F348 |
| Services\IconFactory.cs | 2891 | 1BD6E8EE8651927C49611A680C15368B508AC7DAA11819C50E2D2611360CDA5E |
| Services\ServiceMonitorEngine.cs | 5779 | A8C98409DFF86BA589E023FB8D48EC260B7C5D3F0F6D025C4D1AB979F26B8C89 |
| Setup\SetupSTM\SetupSTM.vdproj | 33877 | 59A179C6AE138F11AD12F9D6405FE67C8A16A5A5DD69BC11736F4421EB57016F |
| Setup\SetupSTM\Debug\setup.exe | 551424 | 4B4D02075DD7D488F82D1F602E81DC2BE0E2AA895DC7532206771FA90BDC93FD |
| Setup\SetupSTM\Debug\SetupSTM.msi | 1353728 | 30A98FF580F36C79E3ADD5488962E915FE5B4DCF37E6BD6DF1CE2040FB51D2D9 |
| Setup\SetupSTM\Debug\SetupSTM.zip | 1293767 | 7515E6F32FD41A14B03E6215765C36FF989DA0FBECF7B17DD9BA6F1E17B3D555 |

## 2. Release 1.0.1 (defect-fix release)

| Item | Value |
| --- | --- |
| Date | 2026-09-13 |
| Scope | DEF-001…DEF-017 (doc 05); no change requests included |
| Assembly version | 1.0.1 (ServiceTrayMonitor.dll FileVersion 1.0.1.0) |
| Build | dotnet build ServiceTrayMonitor.sln -c Release → 0 errors, 0 warnings (BV-01) |
| Automated tests | 38 passed, 0 failed, 0 skipped (doc 06 §4) |
| UAT | Not started (UAT-01…UAT-12) |
| Approval | Pending sponsor sign-off |

### Change inventory versus v1.0.0

| Change | Files |
| --- | --- |
| Modified | app.manifest, README.md, ServiceTrayMonitor.csproj, ServiceTrayMonitor.sln (test project added), TrayAppContext.cs, Forms\CredentialsForm.cs, Forms\ManageServicesForm.cs, Forms\SettingsForm.cs, Models\MonitoredService.cs, Services\ConfigManager.cs, Services\ElevatedServiceRunner.cs, Services\IconFactory.cs, Services\ServiceMonitorEngine.cs, Setup\SetupSTM\SetupSTM.vdproj |
| Added — source | Models\StatusPalette.cs, Models\ServiceSelection.cs, Services\ServiceActions.cs, Services\StartupManager.cs |
| Added — tests | Tests\ServiceTrayMonitor.Tests\ (project + 4 test files) |
| Added — project control | .gitignore, docs\project\ (documents 01–11), graphify-out\ (knowledge base) |
| Added — build output | Setup\SetupSTM\Release\SetupSTM.msi, Setup\SetupSTM\Release\setup.exe |
| Unchanged | Program.cs, Models\StoredCredential.cs, ServiceTrayMonitor.csproj.user, icons, Setup\SetupSTM\Debug\* (still the 1.0.0 installer) |
| Removed | None |

### 1.0.1 file manifest (SHA-256, source and project files)

| File | Bytes | SHA-256 |
| --- | --- | --- |
| app.manifest | 1233 | 58652422A7BA89C832E9AA41D194BF57E2F9B635648D98F7BFE5D439BBEFCE9D |
| Program.cs | 308 | 3D0FD5A2D890CF28C62280D3C54EADDAF1D5BA7E627EBD2CC8FF363664717860 |
| README.md | 5515 | 20DE9BCCD3E361C1D4EA1C9A14E12C221D74A16EC64F88305FE3D40F248D7F2D |
| ServiceTrayMonitor.csproj | 1482 | EC8F855E23C65419FC1EA472D5B3BBE5391FAC4F65EC1C9C0D5585A7383DFDF4 |
| ServiceTrayMonitor.csproj.user | 487 | 2953576DE197F8DCF9DC6B346F98B3B899B77D5C792A511BB7792DF9456D0024 |
| ServiceTrayMonitor.sln | 3945 | F964E3CA5983FC701AC7B3552FD8314082DC9DCD447E7C0D52F85CCBE543B7D5 |
| TrayAppContext.cs | 10700 | 1CAB58BD37A4196DADDC392BC8F9D00C56C58B9C83E75A0FEB3C4E731352954F |
| Forms\CredentialsForm.cs | 8749 | B4DA98F531ABADCBE03CE519A454EC8010FB9499CF640C5D074BA306C476FCAD |
| Forms\ManageServicesForm.cs | 11326 | 7ADB9153C5F22968DC85473D6FBB2D21BE7E005C0160840E447EA7DDB98C83C2 |
| Forms\SettingsForm.cs | 7210 | D3FF85E84312506E63D5FE2A27E81B63926FE81F126231AF638D62FE36BA8B07 |
| Models\MonitoredService.cs | 1786 | 851C46A7F0083A2B491CEA20B269280939FB92957F28A13450D9CA1B3E9FD35B |
| Models\ServiceSelection.cs | 2308 | 747392C328D33A63B025BE59D904A14EAD62C081971AF093D87F94E814DF74DB |
| Models\StatusPalette.cs | 2399 | 2B47E513A5FD9F4D87705F88D2DECBD6528CF30C26218DD75DB5D09DE4605738 |
| Models\StoredCredential.cs | 801 | C28EAB64F8A31C4D279B9C458EA064DA646D42B5E94B2ADF44670D444B795FC7 |
| Services\ConfigManager.cs | 7884 | F94DE96B5758AC8F2C7945CF96AA54F764F1FBF951F10E4A69E78661C1968555 |
| Services\ElevatedServiceRunner.cs | 5887 | 73D32FBEE0A932DED5CACCB83CCE784556F5E2F94A202A6DD13553140DE527D8 |
| Services\IconFactory.cs | 2901 | D38EC652B0A345BC5F18EF6A653863ECA67615B0FF2AC09A2BA46136D497D555 |
| Services\ServiceActions.cs | 4049 | 092DBEA18D5A3C929A75EFEA8304E847B55578039EF4F7C0E28398CB9A74B976 |
| Services\ServiceMonitorEngine.cs | 5965 | 5D9FE1498C706ACD31E8EF062FEE6F5C71D2589C1B39F57464CC27064B638A5E |
| Services\StartupManager.cs | 6241 | 65FB6B3432B1FEFC89DB8EB0395265EF8AD1AD5F34349AAF7611AADCDAFF2F0C |
| Setup\SetupSTM\SetupSTM.vdproj | 33590 | 80B6DA1D990D67E6DC72BB2F8980E09B6C70D3D1D5F8E32C4F8E82D44D9262D9 |
| Tests\ServiceTrayMonitor.Tests\ServiceTrayMonitor.Tests.csproj | 842 | 45F4F42F78C8DD4E24369A1CCC40FE77A8C5956CA43CEC19691B5F96C5083D32 |
| Tests\ServiceTrayMonitor.Tests\ConfigManagerTests.cs | 4148 | D29E71E7B4797EBC762E52BD84F38F9138AC1B359954A945B96F08B6799D85D7 |
| Tests\ServiceTrayMonitor.Tests\ServiceSelectionTests.cs | 2004 | 07C2F684138D6BF70D88B74E678F046220C379AE06E1DEF15B10B677BAE4FBEA |
| Tests\ServiceTrayMonitor.Tests\ServicesTests.cs | 5189 | E9BC146400A5602ACC23C23199EB9C6BF090AE3E2E8ED3DB9E808D106726A0CC |
| Tests\ServiceTrayMonitor.Tests\StatusAndRulesTests.cs | 4342 | AD5E6558078406D1A9BAE1B536F82C32B3CA1F13F7042D4E8319484A146BA660 |

### 1.0.1 installer artefacts

Built 2026-09-13 11:31 with Visual Studio 18 (devenv ServiceTrayMonitor.sln /Build "Release|Any CPU" /Project SetupSTM /ProjectConfig Release).

| File | Bytes | SHA-256 |
| --- | --- | --- |
| Setup\SetupSTM\Release\SetupSTM.msi | 1365504 | A43FCF32E7817D078954697705EC6E849D445EB18212BDA0B172C03E41182757 |
| Setup\SetupSTM\Release\setup.exe | 683520 | 919E5DC017898F58B879886B1D344A1662D0728558CC188543B715D6B2C3AA2B |

MSI properties, read from the built package:

| Property | Value | Check |
| --- | --- | --- |
| ProductName | SystemTrayMonitor | Unchanged (CR-002) |
| ProductVersion | 1.0.1 | ✔ |
| ProductCode | {6E2B7C41-3F9D-4A8E-B5C2-9D17E4A30F58} | ✔ new |
| UpgradeCode | {1B549785-373D-417D-A58F-C1CE513727F4} | ✔ same as 1.0.0 |
| Manufacturer | Miautrix | ✔ |
| Upgrade table | PREVIOUSVERSIONSINSTALLED for versions < 1.0.1 (removes 1.0.0); NEWERPRODUCTFOUND for ≥ 1.0.1 (detect only) | ✔ in-place upgrade |
| Bootstrapper prerequisites | .NET 8 Desktop Runtime (x64) only | ✔ .NET Framework 4.7.2 removed from project; no "v4.7.2" string in setup.exe |

Packaged files: ServiceTrayMonitor.exe, ServiceTrayMonitor.dll, .pdb, .deps.json, .runtimeconfig.json, System.ServiceProcess.ServiceController.dll, icons, README.md.

## 3. Placing the baseline and release in GitHub (client action — WBS 1.3.2)

The folder miautrix-ServiceTrayMonitor is not yet a repository and must not be renamed or moved (DEC-001).

- In the GitHub app, add miautrix-ServiceTrayMonitor as a repository. .gitignore already excludes bin/, obj/, .vs/, and the graphify cache.

- Commit the current state as "Release 1.0.1 — defect fixes DEF-001…DEF-017".

- Create a GitHub Release v1.0.0-baseline and attach the baseline zip (§1) with its SHA-256 in the description. The as-found state is then preserved and auditable without rewriting working files.

- After UAT sign-off, create GitHub Release v1.0.1 and attach SetupSTM.msi and setup.exe (§2).

- Decide whether installer binaries under Setup\SetupSTM\Debug and \Release stay committed or are only published as release assets (recommended: release assets only; then add both folders to .gitignore).

## 4. Release notes — 1.0.1 (draft)

Fixed

- Saving monitored services no longer erases the saved admin credential.

- Filtering the service list no longer loses checks or drops services hidden by the filter.

- "Start automatically when Windows starts" now works: it uses a scheduled task with administrator rights and removes the old, non-working registry entry.

- The credential Test button no longer hangs; it reports whether the account gets a full administrator token.

- With a saved credential, actions no longer fail with "Access is denied". The app uses its own rights first and the saved account only when Windows refuses.

- The UI stays responsive during start/stop/pause/resume; results are reported when the service actually reaches the new state.

- The main window keeps sort order, scroll position, and selection while statuses refresh.

- A missing service shows a gray dot, as documented.

- A damaged settings file is kept as a backup instead of being silently replaced.

- Re-saving the credential without retyping the password keeps the saved password.

- Installer upgrades 1.0.0 in place and no longer asks for .NET Framework 4.7.2.

- Stability: fixed thread-marshalling and resource-leak issues.

Known limitations: no Restart action (CR-001); installed product name "SystemTrayMonitor" (CR-002); unsigned binaries (CR-003).

# 11 — Lessons Learned Register

| ID | Date | Phase | Situation | Lesson / recommendation | Applies to |
| --- | --- | --- | --- | --- | --- |
| LL-01 | 2026-09-13 | Design | The credential feature was designed for non-admin users while the manifest forces elevation. With a credential saved, actions got a UAC-filtered token and failed (DEF-005). | Test security-sensitive features in the exact elevation scenario they target, with a real second account, before release. | Any feature touching elevation or credentials |
| LL-02 | 2026-09-13 | Construction | Redirected child-process output that was never read deadlocked the app (DEF-004). | When redirecting process output, drain stdout and stderr concurrently and apply timeouts. Prefer in-process APIs over shelling out. | All process launches (e.g. StartupManager) |
| LL-03 | 2026-09-13 | Construction | Two windows saved different parts of the same config file from different in-memory copies, and one overwrote the other (DEF-001). | Give persisted state a single owner that re-reads and merges on save; never share mutable settings objects across windows. | Config and any shared state |
| LL-04 | 2026-09-13 | Construction | The UI synchronization context was captured before WinForms installed it (DEF-015). | In an ApplicationContext constructor, install WindowsFormsSynchronizationContext explicitly before capturing it. | Tray/background-thread UI updates |
| LL-05 | 2026-09-13 | Release | v1.0.0 installer settings prevent in-place upgrades (DEF-013). | Decide versioning and upgrade policy (UpgradeCode, RemovePreviousVersions) at the first release. | Installer |
| LL-06 | 2026-09-13 | Project control | Changes began before a version-control baseline existed. | Commit the as-is state before the first change. Until then, a hashed snapshot is the minimum baseline. | All projects |
| LL-07 | 2026-09-13 | Analysis | The knowledge graph surfaced duplicated logic (colour palette, action rules) and the most coupled components (TrayAppContext, ServiceMonitorEngine), which guided where to consolidate. | Build the knowledge base before planning changes and refresh it (/graphify --update) after each release. | Feature planning |
| LL-08 | 2026-09-13 | Quality | 1.0.0 had no automated tests, so regressions were invisible. | Add tests with every fix and CR; keep them non-invasive so they run safely on admin machines. | All changes |